## Sponsor Inputs
# | High level ideas / Features
1 | Create Account
2 | View Restaurants
3 | Search Restaurants
4 | View Menu
5 | Add to Cart
6 | Purchase
7 | Restaurant views order
8 | Restaurant marks order as delivered
Notes:
1 | The above points were listed as draft ideas by the project sponsor.
2 | The project sponsor mentioned that he wants to compete against Talabat.
3 | As a sponsor, I am planning to compete against Talabat.
4 | This is a view only file, you can make a copy then edit in the copy.
5 | You can find a tab named Product Backlog Template, please feel free to use it when creating your product backlog.

## Product Backlog Template
# | Epic | User Story | Priority | Ready to be planned | Planned Sprint | Status
1 | Create Account | As a user , I want to sign up so that I can create account | 1 | Ready
|  | As a user , I want to use Gmail so that I can sign in easily | 1 | Ready
|  | As a user , I want to use mobile authentication so that I can sign in easily | 2 | Ready
|  | As a user , I want to connect app with google map so that app can detect my location | 2 | Ready
|  | As a user , I want to be notified by offers and promo codes so that I can order accordingly | 2 | Ready
2 | View Restaurants | As a user , I want to view restaurants so that I can see the different restaurants available | 1 | Ready
|  | As a user , I want to connect app with google map so that app can detect near by restaurants | 2 | Ready
|  | As a user , I want to view restaurants rating so that I can choose accordingly | 2 | Ready
|  | As a user , I want to categorize restaurants so that I can find my needs easily | 2 | Ready
|  | As a user , I want to notice offers and promo codes by restaurant so that I can order accordingly | 2 | Ready
3 | Search Restaurants | As a user , I want to search restaurants so that I can find specific restaurant | 1 | Ready
4 | View Menu | As a user , I want to view menu so that I can see the different dishes to make a decision what to eat | 1 | Ready
|  | As a user , I want to view best recommended plates so that I can choose accordingly | 2 | Ready
|  | As a user , I want to view price list so that I can choose accordingly | 1 | Ready
5 | Add to Cart | As a user , I want to add to cart so that I can choose multiple items and see the total price | 1 | Ready
|  | As a user , I want to remove items from cart so that I can choose multiple items and see the total price | 1 | Ready
|  | As a user , I want promo codes to be filled auto so that I can order easily | 2 | Ready
6 | Purchase | As a user , I want to purchase so that I can pay for the food I added to the cart | 1 | Ready
|  | As a user , I want to add credit card so that I can pay for the food I added to the cart | 1 | Ready
7 | Restaurant views order | As a restaurant , I want to view orders so that I can start preparing the orders to be out for delivery | 1 | Ready
|  | As a restaurant , I want to view feedbacks so that I can enhance quality | 2 | Ready
8 | Restaurant marks order as delivered | As a restaurant , I want to mark the order as deliverd so that I know that the order last process had finished | 1 | Ready
|  | As a restaurant , I want to view delivery quality and speed so that I can enhance quality | 2 | Ready

## Conduct Planning
Sprint Plannig Keys | Output
Sprint Goal | Compete against Talabat
Availability for this sprint | 2 days per week holidays
1 sick leave per day
1 annual leave per day
Team Capacity | 2 Create Account
2 View Restaurants,Search Restaurants &View Menu
2 Add to Cart & Purchase
2 Restaurant views order & Restaurant marks order as delivered
2 Security
Total 10
Sprint backlog | in the previous tap
Team Confidence | Project will be delivered on time with 1st and 2nd priorities