## Task Board
To Do | In Progress | Testing | Done
S_AGILE_04: Prepare DOR and DOD | S_AGILE_03: Create Task Board & Burndown chart | S_SWCM_01 | S_AGILE_01: Prepare a refined backlog
S_PM_02: Stakeholder Engagement & Communication Plan |  | S_AGILE_02: Conduct Sprint Planning | S_PM_01: Identify Stakeholders
S_PM_03: Create Team Charter
S_PM_04: Create WBS for your project
S_PM_05: Risk Management
S_PM_06: Estimation
S_PM_07: Basic Scheduling
S_PM_08: Scheduling via PDM
S_PM_09: Scheduling via MS Project (Bonus)
S_PM_10: Monitoring via EVM

## Brundown Chart
Days | Ideal Tasks Remaining | Actual Tasks Remaining
1 | 15 | 15
2 | 12 | 13
3 | 9 | 8
4 | 7 | 7
5 | 4 | 5
6 | 2 | 1
7 | 0 | 0